## Report
Issue Register
OmniOps
CONFIDENTIAL
Organisation | OmniOps
Generated by | Mahmoud Abdulaziz <grc.manager@omniops.me>
Generated at | 2026-09-23 10:59 UTC
Visibility | SUBTREE
Document reference | 1906-20260923105957

## Issues
Ref | Entity | Source | Source reference | Engagement | Title | Rating | Status | Raised by | CAP owner | Identified | Target | Age (days) | Overdue by | Escalation
AUD-2026-01-F2 | OmniOps | InternalAudit |  | AUD-2026-01 | Two service accounts had MFA disabled. | Medium | CAPAssigned | Mahmoud Abdulaziz | Ibrahim Abdulaziz | 2026-08-07 | 2026-10-06 | 47
AUD-2026-02-F1 | OmniOps | InternalAudit |  | AUD-2026-02 | Three activities in the marketing workspace lack a recorded basis. | High | CAPAssigned | Ibrahim Abdulaziz | Rami Khalil | 2026-08-19 | 2026-09-18 | 35 | 5
AUD-2026-01-F1 | OmniOps | InternalAudit |  | AUD-2026-01 | Q2 recertification was not completed for two systems. | High | Closed | Mahmoud Abdulaziz | Ibrahim Abdulaziz | 2026-08-19 | 2026-09-18 | 35
ISS-2026-001 | OmniOps | SelfIdentified | RCSA-2026-01 |  | Self-assessed ineffective control: AC-04 | Medium | Open | Rami Khalil |  | 2026-09-15 | 2026-11-14 | 8