## Report
Issue Register
OmniOps
CONFIDENTIAL
Organisation | OmniOps
Generated by | Mahmoud Abdulaziz <grc.manager@omniops.me>
Generated at | 2026-09-24 22:36 UTC
Visibility | SUBTREE
Document reference | 97EF-20260924223621

## Issues
Ref | Entity | Source | Source reference | Engagement | Title | Rating | Status | Raised by | CAP owner | Identified | Target | Age (days) | Overdue by | Escalation
AUD-2026-01-F2 | OmniOps | InternalAudit |  | AUD-2026-01 | Two service accounts had MFA disabled. | Medium | CAPAssigned | Noura Alsuhaimi | Mehdi Tantaoui | 2026-08-08 | 2026-10-07 | 47
AUD-2026-02-F1 | OmniOps | InternalAudit |  | AUD-2026-02 | Three activities in the marketing workspace lack a recorded basis. | High | CAPAssigned | Mehdi Tantaoui | Abdullah Alfifi | 2026-08-20 | 2026-09-19 | 35 | 5
AUD-2026-01-F1 | OmniOps | InternalAudit |  | AUD-2026-01 | Q2 recertification was not completed for two systems. | High | Closed | Noura Alsuhaimi | Mehdi Tantaoui | 2026-08-20 | 2026-09-19 | 35
ISS-2026-001 | OmniOps | SelfIdentified | RCSA-2026-01 |  | Self-assessed ineffective control: PDP-03 | Medium | Open | Hassan Rahman |  | 2026-09-16 | 2026-11-15 | 8